## Timeline
|  | Complete | Dates | Day* | Comments
*when the day falls on a weekend day, use the first weekday prior to the weekend day
I. | Thesis Manuscript | Partially
| 1. First Draft (this is your/student draft and does not need to be submitted) |  | 2023-11-08 | Wednesday
| 2. Send written thesis title page to GCB for review (info.gcb@unibe.ch) |  | 2023-11-08 | Wednesday
| 3. Final Draft (this is the draft to send to supervisor and GCB) |  | 2023-11-22 | Wednesday
II. | Title Page review |  | 2023-11-13 | Monday
Send Title Page for review to GCB Admin 11 weeks prior to oral thesis defense
III. | Inform GCB Admin 10 weeks prior to oral thesis defense: |  | 2023-11-22 | Wednesday
1. planned defense date
2. thesis defense schedule
| 3. if not yet provided, title, name, affiliation and Email address of external co-referee |  | 2023-11-22 | Wednesday
IV. | Provide copy of written thesis 10 weeks prior to defense to:
IV.a. | 1. supervisor (remember to communicate the assessment deadline) |  | 2023-11-22 | Wednesday
| 2. GCB and include the completed PhD Degree form (including reguired publications) to the GCB for plagiarism check |  | 2023-11-22 | Wednesday
IV.b. | 8 weeks (latest) prior to oral thesis defense (GCB Office only) |  | 2023-12-06 | Wednesday
GCB Coordinator sends to external co-referee:
1. written thesis and 2. thesis assessment form
V. | Submit all PhD documents to the GCB office at the very latest, four weeks prior to the specified thesis date |  | 2024-01-03 | Wednesday
1. Study sheet (showing required ECTS, Scientific Integrity, Mid-Term, etc.) printed as a report from KSL, saved in pdf form
2. Postive thesis assessments sent to GCB Coordinator direclty from supervisor and from external co-referee.
VI. | Thesis Oral Defense Date P |  | 2024-01-31 | Wednesday
VII. | Bound thesis Defense - Deliver
| 1. Make appointment. Then drop off 3 bound thesis defense copies to GCB Office. |  | 2024-02-14 | Wednesday
VIII. | Graduation - "PhD Project" Complete
1. Confirmation letter sent to graduate when GCB has received the thesis defense record and the printed and bound copies of the thesis)
| 2. Diploma ready (fully signed) approximately 5 months after succesful defense. Graduate will be notified. |  | 2024-06-19 | Wednesday
2023-11-01
To automatically calculate milestone dates. enter DD.MM.YYYY of planned thesis defense date Column D, Row #27. E.g., in this example, 02/08/2022. When this changes, change only this date to recalculate other dates
Dropdown list to mark status

## Instructions
1. The steps are according to the GCB PhD Thesis Defense process, which can also be found on the GCB Website, page Thesis Defense
2. When this form is used electronically, changing the date in Column D, Row #30 will automatically change the other dates, accordingly
3. Column C, "Complete" contains dropdown menus. Choose Yes, No, Partially and the field will turn green, yellow, or red accordingly to assist with an "at a glance" assessment of overall status
4. Print settings are in place for the current size when this will be used as hard copy

## DropDown List
Yes
No
Partially